## Project Overview
FINAL PACK PROCESS IMPROVEMENT – PROJECT OVERVIEW
Section | Description
Project Name | Final Pack Department Process Optimization
Process Owner | Final Pack Department
Process Engineer | Papa Nii Lamptey
Objective | Increase packing throughput while reducing wasted motion and downtime
Scope | Final Pack operations including material staging, packing, strapping and posting
Start Date
Target Completion
Problem Statement
Repacked dies
Break and time scheduling
Packing material rack cart and strapper cart location
Employee skill level variation
Lack of standardized packing workflow

## Current Process Metrics
Parameter | Value | Unit | Notes
Average time to pack 1 Final Pack | 30 | minutes | Based on time study
IPT packing time | 5 | minutes
Workers per pack team | 2 | people
Available work hours per shift | 6.25 | hours
Total shift minutes |  | minutes

## Capacity Model
Scenario | Pack Time (min) | Packs per Shift | Notes
Current | 30 |  | Baseline
Improved workflow | 25
Material staged | 22
Standard work | 20

## Root Cause Analysis
Category | Possible Causes | Evidence | Impact
Method | No standard packing procedure | Observed during operations | High
Motion | Workers walking to retrieve materials | Time study observation | Medium
Materials | Packing materials not staged | Observed | High
Manpower | Skill level variation | Supervisor feedback | Medium
Machines | Strapper machine availability | Observed | Low

## Improvement Action Plan
Action | Owner | Priority | Expected Impact | Status
Create standard work instruction | Process Engineer | High | Reduce variability
Stage packing materials before job | Supervisor | High | Reduce motion waste
Dedicated strapper cart location | Maintenance | Medium | Faster packing
Operator role separation | Supervisor | High | Better efficiency
Skill training program | HR / Supervisor | Medium | Improved consistency