Maintenance Culture Transformation & Preventive Maintenance Optimization Plan

Prepared for: Director of Operations
Prepared by: Process Engineering
Purpose: Improve maintenance effectiveness, reduce unplanned downtime, and establish a sustainable maintenance culture

1. Executive Summary

The current maintenance system is highly reactive, inefficient, and unsustainable under existing staffing levels. Preventive Maintenance (PM) activities are broad, rushed, and inconsistently executed, while tool organization and planning systems do not support effective maintenance execution.

This proposal outlines a structured, phased maintenance transformation plan focused on:

- Establishing 5S-based tool organization

- Redesigning PMs to be machine-focused

- Separating inspections from repairs

- Introducing planning discipline

- Creating visibility, accountability, and data-driven improvement

The intent is not to increase workload, but to reduce waste, firefighting, and downtime through better planning and execution.

2. Current State Assessment

2.1 Tool Storage & Maintenance Areas

- Poorly organized shelves and tool storage

- No ownership or standardization

- Time lost searching for tools

- Duplicate purchases and missing tools

- Reduced technician efficiency and morale

2.2 Preventive Maintenance Execution

- PMs are structured around entire presses, not individual machines

- Scope exceeds available labor time

- Inspections are rushed or skipped

- Findings are inconsistently documented

- PM effectiveness is low

2.3 PMs and Repairs Are Combined

- Inspections and repairs occur simultaneously

- Leads to incomplete inspections

- Reactive decision-making

- No structured repair planning

2.4 Staffing Reality

- Current PM scope does not align with manpower

- Maintenance team forced into firefighting mode

- Planning time is limited or non-existent

3. Business Impact of Current State

| Impact Area | Consequence |
| --- | --- |
| Downtime | Increased unplanned stoppages |
| Safety | Missed early warning signs |
| Cost | Higher emergency repair costs |
| Labor | Inefficient use of skilled technicians |
| Morale | Low ownership and burnout |
| Data | Poor reliability insight |

4. Target State Vision

Maintenance Philosophy Shift

From: Reactive, press-level PMs
To: Planned, machine-focused, inspection-driven maintenance

Key Principles

- PMs are inspection-focused, not repair-focused

- Repairs are planned, not improvised

- Tools and parts are ready before work begins

- PM scope matches staffing reality

- Maintenance work is visible and measurable

5. Phased Implementation Plan

Phase 1 – Foundation & Engagement (Weeks 1–3)

5.1 Maintenance Reset & Buy-In

Kickoff Meeting

- Maintenance technicians

- Maintenance leadership

- Production representative

- Process Engineering

Objectives

- Align on problems (no blame)

- Explain new PM philosophy

- Capture technician input

- Establish ownership

5.2 5S Tool Storage Reorganization (Pilot)

5S Steps

- Sort – Remove broken, unused, duplicate tools

- Set in Order – Tool homes, shadow boards, machine-based grouping

- Shine – Clean and repair storage areas

- Standardize – Photos, labels, posted rules

- Sustain – Area ownership + weekly audits

Deliverable

- One model maintenance area fully 5S’d

Phase 2 – Preventive Maintenance Redesign (Weeks 2–6)

6.1 Shift to Machine-Focused PMs

Current

- One PM per press

- Excessive scope

- Low quality execution

Future

- Individual PMs per machine

Example – Press Line

- Billet Saw PM

- Billet Oven PM

- Press Hydraulics PM

- Upper Puller PM

- Lower Puller PM

- Run-Out Table PM

- Finishing Saw PM

PM Design Rules

- 30–90 minutes maximum

- Inspection-only

- Focus on known failure modes

6.2 Standard PM Structure

Each PM includes:

- Visual inspection

- Listen / vibration / temperature

- Lubrication checks

- Safety checks

- Condition rating:

  - OK

  - Monitor

  - Action Required

Rule: Repairs exceeding 10–15 minutes are logged, not executed during PM.

Phase 3 – Separation of Inspection & Repair (Critical Change)

7.1 Saturday = Inspection & Planning

Saturday Activities

- Perform PM inspections only

- Capture findings with notes/photos

- Generate work orders

- Identify parts and labor needs

No major repairs unless safety-critical.

7.2 Weekday = Planned Repairs

- Repairs executed during:

  - Planned downtime

  - Changeovers

  - Scheduled maintenance windows

- Jobs are:

  - Pre-approved

  - Parts staged

  - Tools ready

Phase 4 – Planning, Visibility & Control (Weeks 4–8)

8.1 Maintenance Planning Board

Sections:

- Backlog

- This Week

- Today

- Waiting on Parts

- Completed

Each job includes:

- Machine

- Issue

- Estimated time

- Priority

8.2 Risk-Based PM Frequencies

| Equipment | Impact | Frequency |
| --- | --- | --- |
| Finishing Saw | High | Weekly |
| Pullers | High | Weekly |
| Billet Oven | Medium | Bi-weekly |
| Press Hydraulics | High | Monthly |
| Conveyors | Low | Monthly |

Phase 5 – Metrics & Continuous Improvement (Week 8+)

9.1 Key Metrics

- PM completion rate

- PM findings converted to planned work

- Emergency breakdown count

- Downtime Pareto by machine

9.2 Monthly Review

- What PMs prevented failures?

- What failures were missed?

- Adjust PM content accordingly

10. Roles & Responsibilities

| Role | Responsibility |
| --- | --- |
| Maintenance Technicians | PM execution, accurate findings |
| Maintenance Supervisor | Scheduling, backlog prioritization |
| Process Engineering | Data analysis, PM optimization |
| Production | Protect maintenance windows |

11. Risks & Mitigation

| Risk | Mitigation |
| --- | --- |
| Resistance to change | Early involvement & pilot wins |
| Time pressure | Reduced PM scope |
| Staffing limits | Planning-driven execution |
| PM quality drift | Audits & feedback loops |

12. Expected Outcomes

Short-Term (1–2 months)

- Organized tools

- Improved PM quality

- Reduced wasted time

Medium-Term (3–6 months)

- Reduced emergency repairs

- Improved uptime

- Higher technician engagement

Long-Term

- Predictable maintenance workload

- Data-driven reliability improvements

- Sustainable maintenance culture

13. Appendices

Appendix A – PM Inspection Template

Appendix B – 5S Audit Checklist

Appendix C – Maintenance Planning Board Template

Appendix D – PM-to-Work Order Flow

Final Recommendation

Approve a pilot implementation on one press line and maintenance area for 8 weeks, followed by phased rollout plant-wide based on results.