## Project Summary
Project Item | Description
Project Name | Die 4152 Dimension 13 Gap Variation Investigation
Process Owner | Process Engineering
Department | Extrusion
Start Date
Die Number | 4152
Profile Feature | Dimension 13 Gap
Target Dimension
Tolerance
Investigation Objective | Identify causes of dimensional variation and establish stable extrusion conditions
Responsible Engineer
Press Used
Expected Outcome | Stable process window and consistent dimensional control

## Problem Statement
Problem Statement
The aluminum extrusion die 4152 experiences gap variation throughout the profile length. Dimension 13 occasionally falls outside the specified tolerance during production runs. This leads to sorting, rework, and reduced production efficiency. The variation occurs between the front, middle, and end portions of the extrusion run, suggesting potential changes in process conditions, tooling behavior, or thermal conditions during extrusion. The goal of this investigation is to identify the root causes and determine the optimal extrusion parameters that maintain dimensional stability throughout the entire run.

## Investigation Plan
Step | Activity | Responsible | Data Needed | Status
1 | Inspect die geometry and bearing conditions | Tooling | Die inspection report
2 | Verify press alignment and equipment condition | Maintenance | Alignment check
3 | Run controlled extrusion test | Production | Extrusion parameters
4 | Measure Dimension 13 across extrusion run | Quality | Measurement data
5 | Compare front, middle, and end dimensions | Engineering | Measurement analysis
6 | Correlate process parameters with dimension variation | Engineering | Parameter logs
7 | Determine root causes | Engineering | Analysis results
8 | Define optimized process window | Engineering | Validated parameters

## Extrusion Run Data
Run # | Date | Press | Die | Billet Temp | Container Temp | Ram Speed | Puller Speed | Cooling Method | Operator | Notes

## Dimension Measurements
Run # | Profile Location | Dimension 13 Measurement | Spec Min | Spec Max | Status
Front of Run
Middle of Run
End of Run

## Process Parameters
Run # | Billet Alloy | Billet Temp | Ram Speed | Exit Temp | Puller Speed | Air Cooling | Stretcher Force | Ageing Temp

## Root Cause Analysis
Category | Possible Cause | Check Method | Result
Tooling | Die bearing wear | Die inspection
Tooling | Uneven bearing lengths | Die measurement
Process | Ram speed fluctuation | Press data review
Process | Billet temperature variation | Billet logs
Mechanical | Puller tension variation | Puller calibration check
Mechanical | Stretcher alignment issue | Alignment inspection
Thermal | Uneven cooling conditions | Cooling observation

## Analysis Dashboard
Analysis Dashboard - Insert charts such as Gap vs Run Position, Gap vs Ram Speed, and Gap vs Billet Temperature

## Conclusion & Recommendation
Observation | Root Cause | Recommended Action